## Sheet1
Task				01/10/15	02/10/15	15/10/15		01/11/15		15/11/15		01/12/15		15/12/15		01/01/16		15/01/16		01/02/16		15/02/16		01/03/16		15/03/16		01/04/16		15/04/16		01/05/16
RASD
Model verification
Project planning
Cost analysis
Design document
Implementation													Core development						Service and Frontend Development
Code inspection																											c
Module Testing																		Core							b			d	d
Integration testing																				a									e	f
System testing
								1		2		3				4								5		6						7

						Locatelli

						Together

						Fusi

				DEADLINES
				1	RASD
				2	Project planning
				3	Cost analysis
				4	Design document + Core dev
				5	Service dev
				6	Frontend dev
				7	FINAL DEADLINE

				Detailed tasks
				a	core integration
				b	service module and integration testing
				c	final code inspection
				d	frontend module testing
				e	frontend integration
				f	system integration