## Sheet1
Task				01/10/15	02/10/15	15/10/15		01/11/15		15/11/15		01/12/15		15/12/15		01/01/16		15/01/16		01/02/16		15/02/16		01/03/16		15/03/16		01/04/16		15/04/16		01/05/16
RASD
Model verification
Project planning
Cost analysis
Design document
Implementation													Core development						Service and Frontend Development
Code inspection																											c
Module Testing																		Core							b			d	d
Integration testing																				a									e	f
System testing
								1		2		3				4								5		6						7

						Locatelli					DEADLINES							Detailed tasks
											1	RASD						a	core integration
						Together					2	Project planning						b	service module and integration testing
											3	Cost analysis						c	final code inspection
						Fusi					4	Design document + Core dev						d	frontend module testing
											5	Service dev						e	frontend integration
											6	frontend dev						f	system integration
											7	FINAL DEADLINE